## Introduction
This is the Project Tracker
You will use this to track your work on your project. The first step is to identify your team on the Team sheet. Also on the Team Sheet, you will specify the address of your GitHub repository for the project. After that, you will complete the Features sheet, which is a summarized version of the use cases you wrote for the last assignment. In addition to listing summary versions of your use cases, recall that you also listed in your Business Requirements document various resources users will need to use your product, so include as "features" the task of creating such resources so you can allocate time to making them.
Then you will identify, in helpful detail, the tasks you will perform to implement each feature. You have to be detailed here, thinking very clearly about what it will take to pursue each task in terms of time.
AFter that, on the Test Plans sheet, you will describe how you will test that each feature is working. Finally, on the Work Log tab, you will enter entries for each work session you spend building your project. Include links to particular assets in your GitHub respository that I can refer to to see evidence of your work.
The purpose of this sheet is to serve as a guide and a tracking mechanism as you try to build the various features of your project.

## Team
Team Members
Team member name | Email address
Sai Krishna Reddy Karka | SaiKrishnaReddyKar@lewisu.edu
Satyadevi Vundavalli | SatyadeviVundavall@lewisu.edu
Abhivardhan Tammana | AbhivardhanTammana@lewisu.edu
Project GitHub | https://github.com/sai277/skillswap-project
Just list the names and email addresses of the members that comprise this team. If there is only one person, just specify one name and email address.

## Features
Feature List
Feature ID | Feature Name | Feature Description
F1 | User Authentication and Profuile Management | This feature allows users to securely log in and register with role selection. It also enables users to manage their profiles, including updating personal information and preferences.
F2 | Skill and Interest Management | This feature allows users to add, edit, or remove skills for teachers and learning interests for learners. It helps in creating a personalized learning experience.
F3 | Availability Management | This feature enables users to set and manage their availability schedules for skill exchange. It ensures effective time management and coordination between learners and mentors.
F4 | AI based Skill Matching and Search | The AI-Powered Skill Matching leverages cosine similarity with word embeddings to match users based on their skills and availability. Additionally, the Manual Skill Search allows users to manually search for mentors based on skills and availability.
F5 | Secure Messaging System | This feature facilitates private chat between users after a learning request has been accepted. It ensures secure and seamless communication.
F6 | Session Sheduling and Management | This feature allows users to schedule learning sessions, send requests, and manage a calendar view. It streamlines the learning process and keeps track of upcoming sessions.
F7 | Badges and Achievements | This feature awards badges to users based on their learning and teaching achievements. It serves as a motivational tool and recognizes user accomplishments.
F8 | Feedback System | This feature provides a simple thumbs up/down system with optional comments and private feedback. It allows users to share their experiences and improve the learning platform.
F9 | Personalized Dashboard | This feature enables users to track their learning and teaching activities with dynamic elements based on their roles. It provides a comprehensive view of progress and achievements.
F10 | Security and Testing | This feature includes conducting security audits, performing final testing, and ensuring all authentication mechanisms, including Multi-Factor Authentication (MFA), are functioning correctly.
Here we list the specific features of your final project. This is just an alternative way to express what you did for the last assignment. Features are the things your project offers the user, so focus on what the user will experience. What will the user be able to do? How will they interact with what you are building? What will they see when they use what you are building?
For each feature, specify a Feature ID. Perhaps this is just a number, or maybe its a short abbreviation that you'll use to uniquely identify each feature. Then specify a name for the feature that describes cleaerly what it concerns. Finally, offer a very specific but brief description. You already did this in the preceding assignment, but if you weren't specific there, you need to be specific here. Otherwise, you can copy the use case text you wrote in that last assignment. The description you provide here should give us a clear understanding of what the user will be able to do and see and interact with in your product.

## Task Estimation
Task Estimation
Feature ID | Task ID | Task Name | Task Description | Estimated Hours | ID of tasks this depends on | Assigned team members
F1 | T1.1 | Database Setup | Setting up the database schema for user authentication and profile management. | 8 | - | Sai Krishna Reddy
F1 | T1.2 | Authentication System | Implementation of authentication features, including registration, login, and password management. | 10 | T1.1 | Sai Krishna Reddy
F1 | T1.3 | Profile Management | Building profile editing, role update, and account deletion functionalities. | 8 | T1.2 | Satyadevi Vundavalli
F2 | T1.4 | Skill Management | This is to allow users to add, edit, and remove skills. | 8 | - | Abhivardhan Tammana
F2 | T1.5 | Interest Management | Manage learning interests and preferences for learners. | 8 | T1.2 | Sai Krishna Reddy
F3 | T1.6 | Availability Scheduling | Build a system for mentors to set available slots for skill exchange. | 10 | - | Sai Krishna Reddy, Abhivardhan Tammana
F4 | T1.7 | AI Matching Algorithm | Develop a matching algorithm using cosine similarity and word embeddings. | 15 | - | Satyadevi Vundavalli
F4 | T1.8 | Manual Search Functionality | Enable users to manually search for mentors based on skills and availability. | 10 | T4.1 | Abhivardhan Tammana
F5 | T1.9 | Secure Messaging Module | Implement encrypted chat system for communication between learners and mentors. | 15 | - | Sai Krishna Reddy
F6 | T1.10 | Session Scheduling System | Build functionality for sending session requests and managing time slots. | 10 | T5.1 | Satyadevi Vundavalli
F6 | T1.11 | Calendar Integration | Integrate Google/Outlook calendar for smooth session scheduling. | 8 | T6.1 | Abhivardhan Tammana
F7 | T1.12 | Badge Assignment System | Award badges for achievements such as First Session, Frequent Learner. | 8 | - | Abhivardhan Tammana
F8 | T1.13 | Feedback Mechanism | Implement thumbs up/down with comments and private feedback. | 8 | - | Satyadevi Vundavalli
F9 | T1.14 | Dashboard UI Design | Design a personalized dashboard for tracking progress. | 10 | T8.1 | Abhivardhan Tammana, Satyadevi Vundavalli
F9 | T1.15 | Dashboard Data Visualization | Display learning history, badges, and session tracking. | 8 | T9.1 | Sai Krishna Reddy Karka, Abhivardhan Tammana
F10 | T1.16 | Security Audit | Conduct security testing and ensure Multi-Factor Authentication (MFA) is working. | 12 | All previous tasks | Sai Krishna Reddy Karka
F10 | T1.17 | Final QA Testing | Perform overall system testing before deployment. | 10 | T10.1 | All Team Members
Here we list the tasks you estimate will be needed to complete your project (in other words, to implement its features). Each row represents a task.
For each task, specify the ID of the corresponding feature. These should come from the list of features you provided on the Features sheet, so perhaps use an Excel formula to set them. Then specify the ID of this task. Perhaps it's just a number, or maybe it's an abbreviation, or maybe it's a combination of the feature ID and a number or a letter - for example, if the feature ID is 1 and you want to represent that this is the first task for implementing feature 1, perhaps you could set the Task ID as 1.1 or 1.A.
Next, specify a Task Name. It should clearly but briefly describe what this task concerns.
Next, describe clearly what is needed to accomplish this task. What steps will you take to carry it out
Then specify how many hours it will take to complete the task. This is just an estimate at this point. If this task depends on another task being done, indicate the task ID of the task it depends on in the next column. Finally, specify who is responsible for completing the task. This could be multiple team members if two or more people are needed to complete the task.
Make sure you in include in your time estimate for each task some time for testing that the task was done correctly / is producing the right output. A good rule of thumb is to allot an additional amount of about 20% to 25% of the time it took to do a task for testing that it works. You won't be testing every single task, and the test plans on the test plans sheet will connect to the overall features rather than the individual tasks. Nevertheless, if you follow the rule of thumb that 20% to 25% of your work effort should be added for testing, you will be sure to allow the right amount of time for it.

## Test Plans
Test plans
Feature ID | Test ID | Test Name | Test Description | Tester | Successful outcome
F1 | 1.1 | Login Test | Verify user authentication with valid credentials | Sai Krishna Reddy Karka | Secure login and role assignment
F1 | 1.2 | Profile Update Test | Test updating personal information and preferences | Abhivardhan Tammana | Profile updated successfully
F1 | 1.3 | Role Selection Test | Ensure correct role-based access control | Satyadevi Vundavalli | Proper role access
F2 | 2.1 | Skill Addition Test | Add, edit, and remove skills and interests | Sai Krishna Reddy Karka | Skills updated
F2 | 2.2 | Interest Personalization Test | Validate personalized learning experience | Satyadevi Vundavalli | Accurate recommendations
F3 | 3.1 | Schedule Management Test | Set and manage availability schedules | Abhivardhan Tammana | Schedule updated
F3 | 3.2 | Time Coordination Test | Ensure effective coordination between users | Satyadevi Vundavalli | No conflicts
F4 | 4.1 | AI Matching Test | Verify skill matching with cosine similarity | Abhivardhan Tammana | Accurate matching
F4 | 4.2 | Manual Search Test | Validate search functionality | Sai Krishna Reddy Karka | Relevant search results
F5 | 5.1 | Chat Functionality Test | Test private chat after learning request acceptance | Abhivardhan Tammana | Seamless communication
F6 | 6.1 | Session Request Test | Send and accept learning session requests | Sai Krishna Reddy Karka | Successful session creation
F6 | 6.2 | Calendar Management Test | Manage the calendar view and upcoming sessions | Satyadevi Vundavalli | Proper schedule tracking
F7 | 7.1 | Badge Assignment Test | Award badges based on learning achievements | Abhivardhan Tammana | Badge correctly assigned
F7 | 7.2 | Achievement Tracking Test | Track and display user achievements | Satyadevi Vundavalli | Accurate tracking
F8 | 8.1 | Feedback Submission Test | Submit thumbs up/down and comments | Abhivardhan Tammana | Feedback successfully submitted
F8 | 8.2 | Private Feedback Test | Ensure privacy for feedback messages | Sai Krishna Reddy Karka | Confidential feedback
F9 | 9.1 | Dashboard Data Tracking Test | Track learning and teaching activities | Abhivardhan Tammana | Smooth learning and teaching activities
F9 | 9.2 | Dynamic UI Test | Verify dynamic UI elements | Satyadevi Vundavalli | Proper UI response
F10 | 10.1 | Security Audit Test | Perform final security checks | Sai Krishna Reddy Karka | No security vulnerabilities
On this sheet, describe how you will test each feature. Each row represents a test you will conduct. You might have multiple tests for each feature to confirm that that feature is working.
In the first column, specify the ID of the feature listed on the Features sheet that this test corresponds to.
In the Test ID column, give this test a unique id. Perhaps it is a combination of the feature ID and a number or letter or abbreviation for this particular test. For example, if the related feature is ID # 1, and this is the first test for ID #1, perhaps the test ID should be 1.1 or 1.A. But you can choose your own unique id system.
In the Test Name column, specify a clear, concise name for this test.
In the Test Description column, specify a clear, concise, but complete description of how the test will be conducted.
In the Tester column, indicate the names of the people on the team who will conduct the test.
Finally, in the Successful Outcome column, describe how you will know that your work passed this test. In other words, how will know that your work successfully implemented the feature it supports?

## Work Log
Task ID (from Task Estimation Sheet) | Date the work was done | Time spent (hours) | Work done by whom? | Description of what was done (be claar in describing the work you did. A step-by-step description would be good.) | Document on GitHub that provides more detail about what was accomplished through this task.
T1.1 | 20/03/2025 | 8 | Sai Krishna Reddy | We designed the database using Django’s ORM and SQLite to store user profiles, skills, and skill exchange requests. First, we created models for users, skills, and skill-sharing interactions, defining relationships such as many-to-many fields for skills. After defining the models, we generated and applied migrations using Django’s migration commands. We then registered the models in the Django admin panel for easy management. Finally, we tested the database using the Django shell to verify data integrity and ensure proper relationships between models. | https://github.com/sai277/skillswap-project
T1.2 | 23/03/2025 | 10 | Sai Krishna Reddy | We implemented the authentication system using Django’s built-in authentication framework. Our system supports user registration, login, and logout functionalities using a combination of class-based and function-based views. We created custom forms to handle user input, ensuring validation and security. Additionally, we defined URL routes to link authentication views with corresponding templates. To manage user sessions, we enabled session-based authentication. Finally, we tested the system by registering new users, logging in, logging out, and verifying access control for restricted pages. | https://github.com/sai277/skillswap-project
T1.3 | 28/03/2025 | 8 | Satyadevi Vundavalli | We developed a profile management system that allows users to update personal information and manage their skills. We created a profile model linked to Django’s user model using a one-to-one relationship. Custom forms were built to enable users to edit their bio, add skills, and update their availability. We implemented profile views to handle data retrieval and updates. Additionally, we designed templates for a user-friendly interface. Testing involved modifying user details, verifying updates in the database, and ensuring form validation worked correctly. | https://github.com/sai277/skillswap-project
T1.4 | 2025-02-04 | 8 | Abhivardhan Tammana | We developed the skill management feature to allow users to select, update, and manage their professional skills. The interface presents a list of predefined skills that users can easily choose from. Once submitted, the selections are stored and reflected in their profile. We ensured only logged-in users could access this feature, providing a secure and personalized experience. The feature was thoroughly tested by adding, editing, and removing skills to confirm that all updates were correctly saved and displayed. This functionality supports accurate skill-based recommendations and collaboration among users with similar capabilities. | https://github.com/sai277/skillswap-project
T1.5 | 2025-05-04 | 8 | Sai Krishna Reddy | The interest management feature was designed to help users personalize their experience by selecting specific topics or fields they are interested in. A list of predefined interests was presented, and users could easily select or update their preferences. These selections are used to tailor the content and recommendations users receive. Access was restricted to authenticated users to ensure secure usage. We tested the feature by updating different combinations of interests and verifying that relevant suggestions changed accordingly. This functionality helps in delivering a more customized and engaging platform experience for each individual user. | https://github.com/sai277/skillswap-project
T1.6 | 2025-08-04 | 10 | Sai Krishna Reddy, Abhivardhan Tammana, Satyadevi Vundavalli | This week, we implemented the Mentor Availability Scheduling feature as part of our Skill Swap application. We began by designing the front-end layout using HTML and Django template language, creating a clean and intuitive form that allows users to input their available dates and times. We included fields for date, start time, and end time, along with CSRF protection to ensure secure submissions. On the backend, we developed Django models to store the availability slots and created views to handle form submissions, data validation, and storage in the database. We also added functionality to display existing availability slots dynamically and provided a "Remove" option for users to delete any slot. To enhance user experience, we implemented notifications confirming successful slot additions or deletions. We completed two rounds of testing: one to validate the update of schedules and another to ensure effective time coordination between users, confirming no overlapping slots. | https://github.com/sai277/skillswap-project